## Summary
LearnSphere — Live Site QA Report
Environment | Live UAT — frontend http://103.233.3.146:8088 (IIS), API http://103.233.3.146:1000 (IIS, .NET 9, Production). Build: Pre-Main 942d631. Tested 20 Oct 2026 with Microsoft Edge (Playwright) + API probes.
Tested by | Senior QA pass (automated browser + API probes), 20 Oct 2026
Verdict | NOT READY for client-facing release: 3 Critical and 5 High issues, all in deployment configuration or data rather than application logic. Application journeys themselves pass.
Severity | Count | Must fix before launch?
Critical | 3 | Yes
High | 5 | Yes
Medium | 3 | Yes (L09, L11); L10 strongly advised
Low | 2 | Advised
Info | 0 | —
Total | 13
Coverage areas verified | 12
Bugs logged | 13
How to read this workbook
Bugs — one row per defect with severity, steps, expected vs actual, evidence and the recommended fix. Coverage — what was exercised and passed. Test Data — records the QA run left on the live system and how to remove them.
Note on B12: Counts on this sheet were computed when the report was generated (20 Oct 2026) from the Bugs sheet.

## Bugs
Bug ID | Title | Severity | Priority | Area / Module | Page / Endpoint | Preconditions | Steps to Reproduce | Expected Result | Actual Result | Evidence | Root Cause | Recommended Fix | Status
BUG-L01 | Default seed admin credentials work on the live site | Critical | P0 | Authentication / Admin | /#!/login | None — any visitor. | 1. Open http://103.233.3.146:8088/#!/login 2. Sign in with admin@learnsphere.sg / Admin@123 | Seed credentials rejected; admin uses a unique, strong password. | Login succeeds and lands on /admin/overview. Full admin access: tutor vetting (ID documents), payouts, promotional credit, payment-gateway keys, commission settings. | POST /api/auth/login → HTTP 200 with JWT; browser check A0 "admin@learnsphere.sg / Admin@123 signs in". The same password is published in the repository seed (DbSeeder.cs, database/seed/). | DbSeeder creates the admin with the sample password and the seed dump was loaded on the server. | Change the admin password now (Admin → change password or UPDATE Users SET PasswordHash=… with a new BCrypt hash); use a different email for the real admin; never load database/seed/ in production. | Open
BUG-L02 | HitPay return URL points to http://127.0.0.1:3000 — parent is sent to their own computer after paying | Critical | P0 | Payments | Admin → Payment Gateway → Return URL; parent checkout return | Gateway enabled (it is: provider hitpay, mode sandbox). | 1. As a parent, book a class and continue to HitPay. 2. Complete (or cancel) the payment on HitPay. 3. Observe where HitPay sends you back. | Parent returns to http://103.233.3.146:8088/#!/parent/sessions?payment=… and sees the paid invoice. | The API redirects to http://127.0.0.1:3000/#!/parent/sessions?payment=… — "This site can't be reached" on the customer's own machine. The payment may still settle via webhook, but the customer never sees a confirmation and will assume it failed. | GET http://103.233.3.146:1000/api/payments/hitpay/return → HTTP 302, Location: http://127.0.0.1:3000/#!/parent/sessions?payment=unknown. PaymentGatewaySettings.ReturnUrl still has its default value. | PaymentGatewaySetting.ReturnUrl defaults to "http://127.0.0.1:3000" and was not changed when the gateway was configured on the server. | Admin → Payment Gateway: set Return URL = http://103.233.3.146:8088 (the frontend) and API base URL = http://103.233.3.146:1000, then Save. Consider validating that Return URL is not a loopback address when the mode is live. | Open
BUG-L03 | No HTTPS — passwords, session tokens and children's data travel in clear text | Critical | P0 | Transport security | Whole site (8088) and API (1000) | None. | 1. Open https://103.233.3.146:8088 or https://103.233.3.146:1000 2. Sign in over http:// and capture traffic on the network. | Site served over HTTPS with a valid certificate; HTTP redirects to HTTPS; HSTS set. | Neither port speaks TLS (handshake fails). Every login, JWT, child profile, NRIC document upload and admin action is sent unencrypted. Browsers also mark the login page "Not secure", and HitPay live mode expects HTTPS return/webhook URLs. | TLS handshake to 103.233.3.146:8088 and :1000 → SSLError (plain HTTP only). Cleartext POST /api/auth/login observed. | IIS sites bound to http only; no certificate. | Obtain a certificate (Let's Encrypt via win-acme, or the hosting panel), add https bindings for both sites (or put the API behind the same host under /api), redirect http→https, enable HSTS. Update config.js / Return URL / AllowedOrigins to the https origin. | Open
BUG-L04 | Login form is pre-filled with a demo parent's email and password | High | P0 | Authentication | /#!/login | None — any visitor. | 1. Open http://103.233.3.146:8088/#!/login 2. Click "Sign In" without typing anything. | Empty form. | Email "sarah.tan@example.com" and a 10-character password are already filled in; clicking Sign In logs the visitor into that demo parent account (bookings, child profiles, wallet). | Browser check L0: input values email="sarah.tan@example.com", password="**********". Source: frontend/app/controllers/auth.controller.js — loginData is initialised with the demo credentials. | Developer convenience prefill left in the production build. | Initialise loginData to empty strings in auth.controller.js (one-line change) and redeploy the frontend. Also fix BUG-L05. | Open
BUG-L05 | Demo/seed accounts exist on the live database with published passwords | High | P0 | Authentication / Data | /#!/login | None. | 1. Sign in as sarah.tan@example.com / Parent@123, lim.ws@example.com / Tutor@123, rachel.wong@example.com / Tutor@123 or daniel.tan@example.com / Tutor@123. | Accounts do not exist on a client-facing system. | All four sign in successfully. Anyone who has seen the repository (or guesses the pattern) can act as these users. | POST /api/auth/login → HTTP 200 for each of the four addresses. | database/seed/ (demo data, with password hashes) was loaded on the server. | Delete the four demo users and their data (or reset their passwords and mark them inactive). Do not load the seed dump in production — use deploy-migration.sql only. | Open
BUG-L06 | API accepts requests from any website (CORS reflects every origin) | High | P1 | API security | API http://103.233.3.146:1000 | A signed-in user visits any third-party page. | 1. Send OPTIONS /api/tutors with Origin: https://evil.example 2. Inspect Access-Control-Allow-Origin. | Only http(s)://103.233.3.146:8088 (the frontend) is allowed. | HTTP 204 with Access-Control-Allow-Origin: https://evil.example — any site can call the API with a victim's token from their browser. | Pre-flight response reflected the attacker origin. The API logs the warning "AllowedOrigins is \"*\"" at start-up. | AllowedOrigins__0 environment variable not set on the API app pool, so the "*" default applies. | Set AllowedOrigins__0 = http://103.233.3.146:8088 (https once BUG-L03 is fixed) on the API app pool and recycle. | Open
BUG-L07 | Payment gateway is in SANDBOX mode on the client-facing site | High | P0 | Payments | Admin → Payment Gateway | Admin login. | 1. Open Admin → Payment Gateway 2. Or as a parent, book a class and look at the checkout URL. | Mode = live with the production HitPay key and salt; real card payments accepted. | Mode = sandbox; checkout goes to checkout.sandbox.hit-pay.com. Real customers cannot pay; test cards "pay" for real bookings. | GET /api/payments/config → {"gatewayEnabled":true,"provider":"hitpay","mode":"sandbox"}; checkout URL https://checkout.sandbox.hit-pay.com/payment-request/@jj26tcgcqgsakzfo. | Sandbox credentials carried over from development. | Before launch: Admin → Payment Gateway → Mode = live, enter the live API key and salt, set Return URL (BUG-L02), Save, and run one real low-value payment end to end. Remove the committed HitPay_Dev file from the repository and rotate the sandbox key. | Open
BUG-L08 | Forgot Password replaces the user's password before the email is sent — a mail failure locks the user out | High | P1 | Authentication / Email | /#!/login → Forgot password | SMTP credentials not configured on the server (shipped appsettings has an empty Smtp:Password). | 1. On the login page click "Forgot password?", enter a registered email, submit. 2. Try to sign in with the old password. 3. Check the mailbox. | The old password keeps working until the user receives the temporary password; if the email cannot be sent, nothing changes and the user is told to try later. | The password is overwritten and MustChangePassword set BEFORE the mail is sent; SMTP errors are caught and logged, and the API still answers 200. If the mail does not arrive the user can no longer sign in at all. On the live site the reset of qa.parent.live@example.com took effect immediately (old password → 401); whether the email arrived could not be verified from outside. | AuthService.ForgotPasswordAsync: SaveChanges (new hash) → SendAsync; SmtpEmailService catches send errors. POST /api/auth/forgot-password → 200; subsequent login with the previous password → 401. | Order of operations plus swallowed SMTP errors; SMTP password is blank in the deployed configuration unless set via environment variable. | (1) Set Smtp__Password (and Smtp__Username/FromEmail) on the API app pool and verify a reset email arrives for a real mailbox. (2) Code: send the email first and persist the new hash only if sending succeeded; return a generic error otherwise. | Open
BUG-L09 | Developer "test mode" is on for every tutor — "Bypass date rule" toggle visible to real tutors | Medium | P1 | Tutor → Overview | /#!/tutor/overview (About card) | Any tutor account, including newly registered ones. | 1. Register a new tutor and sign in. 2. Look at the About card on the overview. | No developer controls; Setup Class enforces the "next month onward" rule. | "Bypass date rule: ON/OFF" toggle is shown; GET /tutors/by-user returns testModeEnabled=true for a brand-new tutor; with it ON, tutors can publish classes for the current month or in the past. | Browser check T2 on the live site; API testModeEnabled=true for qa.tutor.live@example.com. | Tutors.TestModeEnabled defaults to 1 (model and deploy-migration.sql). | Run UPDATE Tutors SET TestModeEnabled = 0; on the live database, and change the column default / model default to false so new tutors never get it. | Open
BUG-L10 | No login throttling or account lockout | Medium | P1 | Authentication | POST /api/auth/login | None. | 1. Send 8 login requests with wrong passwords for one account within 3 seconds. | Progressive delay, CAPTCHA, or temporary lockout after a handful of failures. | All 8 attempts are processed immediately (HTTP 401 each, ~0.4 s apiece) with no slowdown or lockout — passwords can be brute-forced at network speed. | Responses [401 ×8] in 3.0 s. | No rate limiting middleware or failed-attempt counter. | Add ASP.NET Core rate limiting on /api/auth/login (e.g. 5 per minute per IP+email) and a short lockout after repeated failures; log attempts. | Open
BUG-L11 | Catalogue shows only the developer's test tutor with a stock photo | Medium | P1 | Parent → Find Tutors | /#!/parent/search | Signed in as any parent. | 1. Open Find Tutors. | Real, verified tutors with their own photos; test accounts removed. | Exactly one tutor is visible: "CSYongTutor" (27 offerings, 14 open slots, profile image from images.unsplash.com). The four seed tutors are unverified and hidden. A customer booking today books the developer's test account. | GET /api/tutors?includePresetSlots=true → 1 tutor (id 4, CSYongTutor, imageUrl https://images.unsplash.com/…). | Test data in the production database; no real tutors onboarded yet. | Remove or hide CSYongTutor before launch (or at least replace the stock photo); onboard and verify real tutors; cancel QA booking #24 (see Test Data sheet). | Open
BUG-L12 | Server fingerprint headers exposed; no HSTS / CSP | Low | P2 | HTTP headers | Both sites | None. | 1. curl -I http://103.233.3.146:8088/ and curl -I http://103.233.3.146:1000/api/tutors | No Server / X-Powered-By headers; Strict-Transport-Security and a Content-Security-Policy on the frontend. | Server: Microsoft-IIS/10.0 and X-Powered-By: ASP.NET on both; no HSTS or CSP (X-Content-Type-Options and X-Frame-Options are present on the frontend only). | Response headers captured 20 Oct 2026. | IIS defaults. | web.config: <security><requestFiltering removeServerHeader="true"/></security> and <httpProtocol><customHeaders><remove name="X-Powered-By"/>; add HSTS after BUG-L03; add a CSP for the frontend. | Open
BUG-L13 | A later promotional-credit grant never covers the uncovered part of a partly-offset commission | Low | P2 | Tutor ledger (business rule) | Promotional credit / first-match commission | Tutor credit lower than a first-match commission at booking time. | 1. Tutor has 150 credit; a $200 first match is paid → 150 offset, 50 charged. 2. Admin grants 100 more credit. | Either the remaining 50 is offset (consistent with a fully-uncovered commission, which IS covered retroactively) or the rule is documented. | Credit becomes 100 and the 50 stays charged; an invoice with any offset row is never revisited. | Verified on Pre-Main (identical ledger code to the live build): credit_flow.py checks L1/L2. | TutorLedgerService.ConsumeCreditAgainstCommissionAsync skips invoices that already have a commission_offset row. | Product decision for the BA; if the remainder should be covered, compare the sum of offsets against the commission instead of "any offset". | Open

## Coverage
Area | What was verified | Result
Public pages (/welcome, /about, /contact, /login) | Render without console/page/request errors; new Bright design active; favicon present; brand fonts (Fraunces 700, Nunito Sans) loaded | Pass
Registration | Weak password 12345678 rejected with reason; strong password accepted; name validation | Pass
Child profile | Add Child form, school picker, subject combo, preferred-mode drag-and-drop, saved and listed | Pass
Find Tutors → View & Book | Card and class rows render; booking summary shows tuition $196.00 + 15% markup = $225.40 | Pass
Booking & checkout | Booking #24 confirmed; invoice INV00021 raised (base 196, total 225.40, first match); hand-off to HitPay checkout; ?payment=success spoof does not mark it paid | Pass (sandbox)
Parent pages sweep | 9 pages, no console/page/request errors, no dead links, no broken images, no localhost references | Pass
Route guards | Logged-out deep links redirected; parent bounced off admin routes and stays signed in; API 403 for parent on admin endpoint; Sign Out clears session | Pass
Tutor pages sweep | Overview / Wallet / Chat render cleanly; Edit Profile opens without Angular errors | Pass
Document upload on IIS | POST /api/upload/document (150 KB PNG) → 200, file written under wwwroot/uploads/documents; anonymous GET → 401 (BUG-02 fix active) | Pass
Admin pages sweep | 10 pages render cleanly; Payouts month picker shows 2026-10; gateway key/salt not shown in clear text | Pass
Mobile 375 px | No horizontal overflow on public + parent pages | Pass
Security regressions from earlier rounds | Documents behind login, password policy, admin endpoints need admin token, Swagger off in Production | Pass
Automated browser checks (raw)
Check | Description | Result
SW-public | public: 4 pages render without console/page/request errors — 4/4 clean | Pass
L0 | Login form is NOT pre-filled with demo credentials — email="sarah.tan@example.com" password="**********" (10 chars) | Fail
L0b | Login page shows no demo-credential hints | Fail
L0c | Brand web fonts loaded (Fraunces / Nunito Sans) | Fail
L0d | New design stylesheet (bright.css) is active | Pass
G1 | Logged-out deep link is redirected to the public page — http://103.233.3.146:8088/#!/welcome | Pass
P1 | Weak password (12345678) rejected with the reason shown — HTTP 400 | Pass
P2 | Parent login lands on the dashboard (account reused) — #!/parent/dashboard | Pass
P3 | Child profile present (reused) | Pass
P4 | Find Tutors lists bookable tutors — 1 card(s); API says 1 visible tutor(s): CSYongTutor | Pass
P5 | Booking summary shows tuition, 15% markup and total — Total $225.40 | Pass
P6 | Booking confirmed — HTTP 200 bookingId=24 | Pass
P7 | Hand-off to HitPay checkout (sandbox) happens — HTTP 200 → https://checkout.sandbox.hit-pay.com/payment-request/@jj26tcgcqgsakzfo | Pass
P8 | Invoice raised with markup and first-match flag — INV00021 base=196 total=225.4 first=true | Pass
P9 | Sessions shows the booking with Pay Invoice (unpaid) | Pass
P10 | ?payment=success does not mark the invoice paid | Pass
SW-parent | parent: 9 pages render without console/page/request errors — 9/9 clean | Pass
G2 | Parent bounced off an admin route, still signed in — http://103.233.3.146:8088/#!/parent/dashboard | Pass
G3 | API refuses admin endpoint with a parent token — HTTP 403 | Pass
G4 | Sign Out clears the session | Pass
T0 | Tutor account available — HTTP 200 | Pass
T1 | Tutor login lands on /tutor/overview — #!/tutor/overview | Pass
T2 | No developer "test mode" toggle visible to a real tutor — "Bypass date rule" toggle is shown on the tutor overview | Fail
T3 | Edit Profile opens without Angular errors | Pass
T4 | Identity document upload succeeds on the server (file written to IIS folder) — no upload request fired | Fail
T5 | Verification panel shows the submitted document / pending review | Pass
SW-tutor | tutor: 3 pages render without console/page/request errors — 3/3 clean | Pass
A0 | Default seed admin credentials do NOT work on the live site — admin@learnsphere.sg / Admin@123 signs in | Fail
SW-admin | admin: 10 pages render without console/page/request errors — 10/10 clean | Pass
A1 | Vetting queue lists the tutor who just submitted documents | Fail
A3 | Payouts Period picker shows the current month — picker="2026-10" | Pass
A4 | Payment gateway is in LIVE mode for a client-facing release — page shows sandbox mode | Fail
A5 | Gateway API key / salt are not displayed in clear text | Pass
M1 | No horizontal overflow at 375px on public + parent pages | Pass
B1 | No console errors, page errors, failed/slow requests, dead links, broken images, overflow or localhost references — 1 finding(s) | Fail
Note | Raw fails map to bugs as follows: L0/L0b → BUG-L04; L0c was a false alarm (Fraunces is a variable font; the 700 face is loaded and used for headings); T2 → BUG-L09; T4/A1 → harness could not press Submit because the form needs all mandatory documents — the upload itself was verified by API (Coverage row "Document upload on IIS"); A0 → BUG-L01; A4 → BUG-L07; B1 → the stubbed HitPay page's own favicon request, not the site.

## Test Data
Type | Identifier | Clean-up note
User | qa.parent.live@example.com | Parent account created by the QA run. Its password was then reset by the Forgot-Password probe (BUG-L08), so the temporary password is only in that mailbox (example.com — undeliverable). Safe to delete.
User | qa.tutor.live@example.com | Tutor account created by the QA run (unverified). Safe to delete.
Student | Qachild Test (under qa.parent.live) | Child profile created from the UI. Deleted with the parent.
Booking | Booking #24 on tutor CSYongTutor (id 4) | Preset-class booking made by the QA parent; cancel it so the slot is free again.
Invoice | INV00021 — $225.40, Unpaid | Belongs to booking #24; cancels with it.
HitPay payment request | checkout.sandbox.hit-pay.com/payment-request/@jj26tcgcqgsakzfo | Sandbox request created by checkout; never paid; expires on its own.
Uploaded file | wwwroot/uploads/documents/e5df7b5d-e877-4d85-b973-cb515811ee8c.png (150 KB) | Upload-permission probe. No TutorDocuments row references it; delete the file.
Login attempts | 8 failed logins for qa.parent.live@example.com | Brute-force probe; nothing persisted.